## Sheet1
Homeless Strategy Action Plan for SSDC 2013 to 2016
Completed
Inprogress
Overdue
Not applicable to SSDC
Not yet started still within timescale
Action No | Action | Outcome | Performance Measure | Timescale | Responsible organisation | Related Goal(s) | Performance Status | Acheivements | Issues | Actions | Next Quarter Forecast
1 | West Somerset District Council and Mendip District Council consider a scheme for non-priority bonds | Every LA has a scheme that offers a non-priority bond. | Creation of a non-priority bond scheme | 2014-01-01 | West Somerset DC & Mendip DC | 1 | Not applicable for SSDC
2 | To consider a rent in advance scheme for non-priority homeless households | Every LA has a rent in advance scheme for non-priority applicants | Creation of a rent in advance scheme for non-priority homeless households | 2014-01-01 | 5 LAs | 1 | Completed with funding from Rough Sleepers Funding
3 | To create more direct access services and facilities for rough sleepers in areas of Somerset where this is lacking. | An increase in the number of direct access facilities and support services for rough sleepers in all areas across Somerset. | Facilities and support in place for rough sleepers | 2016-06-01 | All 5 LA Partners in-conjunction with the Avon and Somerset Rough Sleepers Group | 1,2 | Progress being made | DX approval to go ahead with Day Centre in South Street | Need to receive funding from Rough Sleepers Group Need to obtain planning permission
SCC through the delivery of the P4A
4 | To attend The Avon and Somerset Rough Sleepers Steering Group | Working with Avon and Somerset Rough Sleepers Steering Group action plan is supported by LAs | The number of actions achieved or in progress from the Avon and Somerset Rough Sleepers Group where they are related to the Local Authority | On-going | 5 LAs | 1,3 | Ongoing progress being made and monitored through the ASRS Group
5 | To ensure Tenant Accreditation Schemes (TAS)are available across Somerset and the outcomes are broadly the same | Effective and consistent accredited schemes across Somerset. | Monitor the number of TASs achieved by each LA | 2014-01-01 | 5 LAs | 2 | Waiting for an update from KHA
Number of actions taken to raise awareness of TAS with private and social landlords.
|  | Private and social landlords are aware of TAS |  |  |  |  | Requested KHA to attend l-lord forum but they were unable to attend at short notice |  |  | To ask KHA to attend the next l-lord forum
2014-01-01
Each District offers a TAS which has a Somerset Kite mark.
6a | To provide clear information to private landlords and applicants on the incentives available to them for private sector housing | A directory of incentives including eligibility criteria is launched. Links on the 5 Local Authority websites to all Local Letting Agency’s across Somerset | Number of applications for the incentives | Jan 2014 and annually updated | Private sector teams in all 5 LAs and housing options/housing welfare teams in all 5 LAs where applicable. | 2
Links placed on LA websites at launch of LLA
6b | Where possible offer consistent incentives across Somerset to make access easier for private landlords | Consistent incentives offered to private landlords across Somerset |  | 2014-01-01 | Private sector teams in all 5 LAs and housing options/housing welfare teams in all 5 LAs where applicable. | 2 | Overdue |  |  | To discuss at next HMG 06/05/2014
Regular assessment to ensure incentives are similar
7 | To consider creating an empty homes action plan which sets out how the LA will bring empty homes back into use to help those on the housing register or threatened with homelessness | Every LA has an empty homes action plan. | The number of empty homes bought back into use in each Authority | 2014-01-01 | Empty Homes Officers across 5 LAs | 2 | Joint strategy produced with MDC
8 | To ensure staff have relevant and consistent training across Somerset | Staff have the appropriate knowledge and skills | Review of case work. | Ongoing | All 5 LAs | 2 | Ongoing
9 | To identify the type and location of temporary accommodation within each LA. Findings to be passed to Strategic Housing. | Up-to-date register of temporary accommodation created. | Production of a register of temporary accommodation | On-going | 5 LAs | 2 | Completed as we have a TA strategy in place and regular meetings with Strategiuc Housing to meet our needs
Issues identified and addressed by Strategic Housing
10 | Preventing young people from becoming homeless by creating a single point of access (HUB). | Single point of access (HUB) established in each LA area | HUBs delivered in each LA area | 2013-12-01 | All 5 LAs and SCC | 2,3 | Completed
| Work within schools and colleges to provide young people with information on what to do in a housing crisis (including how to access Homefinder Somerset)s | Working with schools and colleges via P2I | The number of P2I advice sessions delivered to schools and colleges
2014-01-01
11 | To review the DHP policy. To ensure DHP is being utilised in the best way for each Authority | DHP policy reviewed and where appropriate changes implemented. |  | 2014-02-01 | 5 LAs Housing Teams and Revenues and Benefit Teams | 3 |  |  |  | To arrange meeting with HB to discuss
The number of awards of DHP to households threatened with homelessness
12 | To create a protocol with private sector landlords to ensure early intervention to prevent tenants being evicted | A private sector pre-eviction protocol |  | 2014-06-01 | HMG to co-ordinate | 3
The number of private sector landlords that have signed up to the protocol.
13 | To consider introducing a policy to prevent illegal evictions | Every LA to have a policy that prevent illegal evictions. | Creation a policy that prevents illegal evictions | 2014-09-01 | 5 LAs – coordinated by HMG. | 3
The number of illegal evictions
14 | To review Somerset pre-eviction protocol for registered providers and re launch. | Launch revised pre-eviction protocol | Review completed by each LA.The number of evictions (this is not necessarily an indication of the performance of the protocol) | 2013-12-01 | 5 LA partners | 3 | Completed within SSDC Area and works well. Was a need for a re-launch as already working well
HMG to coordinate
15 | To ensure planners and enablers are aware of lack of 1 /and2 bedroom properties by providing evidence from Homefinder Somerset. | Increase the provision of 1 and 2 bedroom social housing properties by the end of 2016. | That evidence from Homefinder Somerset has been taken into consideration by planners and enablers | Ongoing annual review | 5 LAs coordinated via HMG | 3 | Ongoing but already raised ith enabling team via Colin McDonald
16 | To encourage shared applications to Homefinder Somerset enabling single people to make joint applications to improve their opportunity to secure social housing. | Improved opportunities for single people on the housing register to access social housing accommodation | The number of shared applications to Homefinder Somerset | 2014-01-01 | Homefinder Somerset partner RPs and 5 LAs | 3 | Completed through the introduction of the revised HFS policy Feb 2014
| To encourage landlords to take a flexible approach when providing accommodation for single person people. |  |  |  | Raise via CBL WG and also at HFS Monitoring Board |  | Raised at last HFS Monitoring Board. L-lords agreed to consider other options
|  | Registered Providers (RPs) taking a flexible approach to letting accommodation to single people wishing to share accommodation. | The number of shared applicants housed through Homefinder Somerset |  |  |  | Difficult to monitor
2014-01-01
17 | To ensure registered providers are not skipping applicants for anti-social behaviour when it occurred more than two years ago. | Homefinder Somerset Monitoring board to review data on a regular basis and take any necessary action | Review conducted and action taken where relevant | 2014-10-01 | CBL WG and Mon board | 3
The number of cases reviewed
18 | To create a protocol with hospitals and the Community Mental Health Team to ensure patients are not discharged from hospital without suitable accommodation | Launch protocol | Reduction in numbers of clients discharged hospitals presenting to homeless departments without prior warning. | 2014-01-01 | HMG to coordinate | 3 | In progress however proving very difficult to get CMHT to engage |  | Difficulty getting CNHT to engage | SSDC and MDC still hope to pilot a link worker utilising funding from the RS Group
5 LAs, Taunton CAB and CMHT
Avon and Somerset Rough Sleepers Steering Group
19 | To create a protocol with the Prison and Police to ensure people are not release from prison/custody without suitable accommodation | Launched protocol | Reduction in the number of clients released from prison/custody presenting to homeless teams without prior warning | 2015-06-01 | HMG to co-ordinate with Police and prison services | 3